Valore Registry

AIA Form Pack · Construction Draw Reference

A field reference for AIA G702 / G703 draw applications. The XLSX tracker is the operational tool; this guide explains the documents and the typical draw cycle.

IP DISCIPLINE

This document does NOT reproduce copyrighted AIA forms. Users must obtain official AIA forms (G702, G703, A101, A201, G701) from the AIA directly (www.aiacontracts.com). This guide is a tracker, checklist, and explanatory reference around the use of those forms — not a substitute.

1 · COMMON AIA DOCUMENTS

G702 Application and Certificate for Payment — single-page payment app

G703 Continuation Sheet — line-item Schedule of Values supporting G702

G701 Change Order — modifications to contract

A101 Standard Form of Agreement (Owner-Contractor) — stipulated sum

A201 General Conditions

Conditional lien waivers — release upon payment

Unconditional lien waivers — release after payment cleared

Stored materials backup (bill of sale, insurance, photos, bonded location)

Architect certification (typically part of G702)

2 · HOW A DRAW PACKAGE WORKS

Sponsor compiles G702/G703 + supporting docs + photos

Architect reviews and certifies G702

Lender consultant inspects site, validates % complete

Lender reviews + approves

Funds wire 4-6 weeks after end of draw period

3 · WHAT TO REVIEW (PER DRAW)

G702 totals match G703 line-item totals

% complete claimed matches inspector's independent estimate

All vendors above threshold provided conditional lien waivers

Prior draw's unconditional lien waivers received

Change orders approved by both owner and lender

Stored materials bonded, insured, with bill of sale

Schedule of values matches updated budget

Retainage tracked correctly per loan agreement

4 · COMMON RED FLAGS

Overfunded line items (>% complete vs % funded)

Missing or delayed lien waivers

Unapproved change orders charged in current draw

Stored materials without insurance or bill of sale

Retainage held below loan agreement threshold

Subcontractor lien claims

Schedule slippage (months behind original timeline)

Budget variance accumulated >5% without explanation

5 · LENDER APPROVAL CHECKLIST

G702 with architect certification

G703 schedule of values (full continuation)

Conditional lien waivers for current draw period

Unconditional lien waivers for prior draw period

Stored materials report + photos + bonded location proof

Inspection report from lender consultant

Updated SOV and current contract sum

Current construction schedule (% complete, days remaining)

Change orders approved (owner + lender) — none pending unfunded

6 · SPONSOR SUBMISSION CHECKLIST

G702/G703 prepared by GC, reviewed internally

All supporting waivers organized by vendor

Stored materials documentation complete

Updated budget + schedule attached

Cover letter explaining any line-item variances

Submitted to architect 5 business days before lender deadline

7 · SAMPLE DRAW FUNDING MEMO TEMPLATE

Draw # · date · project name

Draw requested ($)

Items held back ($) — reason

Recommended funding ($)

Budget status (revised contract, % complete, schedule status)

Major risks identified

Recommendation (Fund / Fund-with-holdback / Hold)

Lender signatures (3 lines)

Valore Registry · AIA Form Pack · v1.0 · Confidential