## Instructions
AIA Draw Tracker · Instructions
Version 1.0
1. Enter draw details on Draw Summary tab.
2. Schedule of Values tracks per-line-item progress.
3. Change Orders tab logs every CO with approval status.
4. Lien Waivers tab matches waivers to draw amounts.
5. Stored Materials tab tracks off-site storage.
6. Inspection tab logs the consultant's findings.
7. Funding Memo tab prints to one letter page for lender approval.
DISCLAIMER: This template does NOT reproduce copyrighted AIA forms.
Obtain official AIA forms (G702 + G703) from the AIA directly.

## Draw Summary
Draw Summary
Top-line draw application. Matches G702 cover sheet.
DRAW DETAILS
Project | Latham Mews
Borrower | Latham Mews LLC
Contractor | Charlotte Builders Group
Draw number | 3
Draw date | 2027-01-15
Original contract sum | 42000000
Approved change orders | 85000
Revised contract sum | 42085000
Work completed to date | 11500000
Stored materials | 480000
Retainage held | 1198000
Previous payments | 6500000
COMPUTED
Current payment due | 0
Remaining contract balance | 0
% complete (revised contract) | 0%

## SOV
Schedule of Values
Per-line-item budget · previous · current period · total · retainage. Mirrors G703.
Line item | Orig budget | Appr changes | Revised | Prev work | Curr period | Stored mat | Total to date | % complete | Retainage
Site work | 8500000 | 0 | 0 | 6800000 | 750000 | 0 | 0 | 0% | 0
Foundation | 4200000 | 0 | 0 | 4200000 | 0 | 0 | 0 | 0% | 0
Structure / shell | 12500000 | 0 | 0 | 3750000 | 3125000 | 0 | 0 | 0% | 0
MEP | 8100000 | 25000 | 0 | 810000 | 2025000 | 120000 | 0 | 0% | 0
Interior finishes | 6700000 | 60000 | 0 | 0 | 0 | 300000 | 0 | 0% | 0
Site improvements | 2000000 | 0 | 0 | 400000 | 600000 | 60000 | 0 | 0% | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0

## Change Orders
Change Order Tracker
CO # | Description | Amount | Status | Owner approved | Lender approved | Budget impact | Notes
1 | MEP routing change — sprinkler upgrade | 25000 | Approved | 2026-11-15 | 2026-11-20 | +0.06% | Code-driven
2 | Interior finishes upgrade — kitchens | 60000 | Approved | 2026-12-10 | 2026-12-15 | +0.14% | Marketing-driven

## Lien Waivers
Lien Waiver Tracker
One row per waiver. Collect conditional waivers before funding; unconditional waivers at next draw.
Draw # | GC / Prime contractor | Subcontractor / vendor | Amount | Type | Date received | Notes
3 | Charlotte Builders Group | Site work sub | 750000 | Conditional | 2027-01-10
3 | Charlotte Builders Group | Foundation sub |  | Conditional | 2027-01-10
3 | Charlotte Builders Group | MEP contractor | 2025000 | Conditional | 2027-01-10 | Draw 3 period
3 | Charlotte Builders Group | Interior finishes sub |  | Conditional |  | No work this draw
3 | Charlotte Builders Group | Site improvements sub | 600000 | Conditional | 2027-01-10
2 | Charlotte Builders Group | Site work sub | 6800000 | Unconditional | 2027-01-10 | Draw 2 final
2 | Charlotte Builders Group | Foundation sub | 4200000 | Unconditional | 2027-01-10 | Draw 2 final

## Inspection
Inspection Tracker
Log each lender consultant inspection. Independent % complete must reconcile with SOV before funding.
Date | Inspector | Findings | Issues noted | Resolution | Approval status
2027-01-12 | Lender Consultant Y | Site work 90% complete; structure 30% per plans; MEP rough-in started. | Stored materials documentation incomplete for MEP | Sponsor to provide bill of sale + bonded location cert | Conditional approval
2026-10-20 | Lender Consultant Y | Foundation 100%; site work 80%. | None | N/A | Approved

## Funding Memo
Draw Funding Memo
Single-page lender approval memo.
DRAW IDENTIFICATION
Project | 0
Draw number | 0
Draw date | 0
PAYMENT
Draw requested | 0
Items held back (separate) | 150000
Recommended funding | 0
BUDGET STATUS
Revised contract | 0
% complete | 0%
Months ahead/behind schedule | +0
RECOMMENDATION
Status | Fund with holdback
Hold reason | Stored materials documentation pending