## Instructions
Lender Checklist · Instructions
Version 1.0 · 2026-05-21
DEAL CONFIGURATION
Loan type | Construction
Property name | Latham Mews
Sponsor | Latham Capital Partners
Target close date | 2026-07-30
STATUS LEGEND
Needed | Identified but not yet requested
Requested | Sent to owner; awaiting response
Received | Received but not yet reviewed
Reviewed | Reviewed by analyst / counsel
Uploaded | In data room; lender-accessible
N/A | Not applicable to this loan type
REQUIRED-VS-OPTIONAL LEGEND
R | Required for this loan type
O | Optional / recommended
- | Not applicable to this loan type
HOW TO USE
1. Set Loan type above — drives the R/O/- column on the Master Checklist.
2. Walk through the Master Checklist tab. Set status on each row.
3. The Document Tracker tab filters to non-N/A items, sorted by due date.
4. Drive the weekly status call from the Missing Items tab.
5. Log every lender question in the Lender Q&A tab.
6. Every submission goes in the Submission Log.

## Master Checklist
Master Checklist
Every item, every loan type. R/O/- driven by the loan type set on Instructions.
# | Item | Category | Req? | Status | Owner | Due | Received | Data room? | Notes
1 | Deal summary | Executive | R | Reviewed | Sponsor | 2026-05-10 | 2026-05-08 | Y
2 | Property overview | Executive | R | Reviewed | Sponsor | 2026-05-10 | 2026-05-08 | Y
3 | Sources & uses | Executive | R | Reviewed | Sponsor | 2026-05-10 | 2026-05-08 | Y
4 | Loan request | Executive | R | Reviewed | Broker | 2026-05-10 | 2026-05-08 | Y
5 | Business plan summary | Executive | R | Reviewed | Sponsor | 2026-05-12 | 2026-05-10 | Y
6 | Capital stack | Executive | R | Reviewed | Sponsor | 2026-05-12 | 2026-05-10 | Y
7 | Timeline | Executive | R | Reviewed | Broker | 2026-05-14 | 2026-05-13 | Y
8 | Exit strategy | Executive | R | Received | Sponsor | 2026-05-15 | 2026-05-14 | Y | Refinance via miniperm
9 | Key risks and mitigants | Executive | R | Received | Sponsor | 2026-05-15 | 2026-05-14 | Y
10 | Sponsor bio | Executive | R | Received | Sponsor | 2026-05-12 | 2026-05-10 | Y
11 | Property address | Property | R | Received | Sponsor | 2026-05-15 | 2026-05-13 | Y
12 | Parcel IDs | Property | R | Received | Sponsor | 2026-05-15 | 2026-05-13 | Y
13 | Site plan | Property | R | Reviewed | Sponsor | 2026-05-15 | 2026-05-12 | Y
14 | Survey | Property | R | Requested | Surveyor | 2026-06-15 |  | N | ALTA survey ordered 2026-05-15
15 | Zoning report | Property | R | Reviewed | Sponsor | 2026-05-18 | 2026-05-15 | Y | MF-zoned, no variance needed
16 | Floor plans | Property | R | Received | Architect | 2026-05-18 | 2026-05-17 | Y
17 | Unit mix / rent roll | Property | O | N/A |  |  |  |  | Construction — no rent roll
18 | Property photos | Property | R | Received | Sponsor | 2026-05-15 | 2026-05-13 | Y
19 | Property management information | Property | - | Needed | Sponsor | 2026-06-01 |  | N | Property mgr selected; agreement TBD
20 | Leasing status | Property | O | N/A
21 | Appraisal (existing) | Property | O | N/A |  |  |  |  | New construction
22 | Environmental Phase I | Property | R | Requested | Phase I provider | 2026-06-10 |  | N | Phase I engaged 2026-05-14
23 | Property condition report (PCA) | Property | - | N/A |  |  |  |  | New construction
24 | T-12 operating statement | Financial | - | N/A |  |  |  |  | New construction
25 | YTD operating statement | Financial | - | N/A
26 | Historical operating statements (3yr) | Financial | - | N/A
27 | Current rent roll | Financial | - | N/A
28 | Stabilized pro forma | Financial | R | Reviewed | Analyst | 2026-05-15 | 2026-05-13 | Y | From UW Workbook
29 | Capex budget | Financial | - | N/A
30 | Construction budget | Financial | R | Reviewed | Sponsor | 2026-05-15 | 2026-05-13 | Y | $60.1M TPC
31 | Sources & uses (detailed) | Financial | R | Received | Sponsor | 2026-05-15 | 2026-05-13 | Y
32 | Tax bills (current) | Financial | R | Received | Tax assessor | 2026-05-20 | 2026-05-18 | Y
33 | Insurance quotes | Financial | R | Requested | Insurance broker | 2026-06-05 |  | N | 3 carriers solicited
34 | Utility bills | Financial | - | N/A
35 | Acquisition / refi / construction purpose | Business plan | R | Reviewed | Sponsor | 2026-05-15 | 2026-05-12 | Y
36 | Renovation plan | Business plan | - | N/A
37 | Leasing plan | Business plan | R | Received | Sponsor | 2026-05-20 | 2026-05-18 | Y
38 | Stabilization timeline | Business plan | R | Reviewed | Sponsor | 2026-05-20 | 2026-05-18 | Y | Year-3 stabilization
39 | Permitting status | Business plan | R | Received | Sponsor | 2026-05-15 | 2026-05-12 | Y | All permits in hand
40 | Construction timeline | Business plan | R | Reviewed | GC | 2026-05-22 | 2026-05-20 | Y | 36-month schedule
41 | Draw schedule | Business plan | R | Received | GC | 2026-05-22 | 2026-05-20 | Y
42 | Sensitivity analysis | Business plan | R | Reviewed | Analyst | 2026-05-20 | 2026-05-18 | Y | From UW Workbook
43 | Sponsor bio (detailed) | Sponsorship | R | Reviewed | Sponsor | 2026-05-12 | 2026-05-10 | Y
44 | Track record | Sponsorship | R | Reviewed | Sponsor | 2026-05-12 | 2026-05-10 | Y | 14 deals
45 | Personal Financial Statement (PFS) | Sponsorship | R | Received | Sponsor | 2026-05-12 | 2026-05-10 | Y | PFS as of 2026-04-30
46 | REO schedule | Sponsorship | R | Received | Sponsor | 2026-05-12 | 2026-05-10 | Y | 8 properties
47 | Organizational chart | Sponsorship | R | Reviewed | Counsel | 2026-05-12 | 2026-05-10 | Y
48 | Entity documents | Sponsorship | R | Received | Counsel | 2026-05-15 | 2026-05-12 | Y
49 | Guarantor financials | Sponsorship | R | Received | Sponsor | 2026-05-12 | 2026-05-10 | Y
50 | Resume / project experience | Sponsorship | R | Reviewed | Sponsor | 2026-05-12 | 2026-05-10 | Y
51 | References | Sponsorship | R | Needed | Sponsor | 2026-06-05 |  | N | References list pending
52 | Appraisal (lender-ordered) | Third-party | R | Requested | Appraiser | 2026-06-15 |  | N | Lender ordered 2026-05-18
53 | Environmental Phase I (lender-reviewed) | Third-party | R | Requested | Phase I provider | 2026-06-10 |  | N
54 | PCA (lender-ordered) | Third-party | - | N/A
55 | Zoning report (lender-ordered) | Third-party | R | Requested | Zoning consultant | 2026-06-08 |  | N
56 | Survey (final certified) | Third-party | R | Requested | Surveyor | 2026-06-15 |  | N
57 | Title commitment | Third-party | R | Received | Title co | 2026-05-25 | 2026-05-22 | Y
58 | Insurance consultant review | Third-party | R | Requested | Insurance consultant | 2026-06-12 |  | N | Lender-required
59 | Seismic report | Third-party | O | N/A
60 | Market study | Third-party | R | Requested | Market study consultant | 2026-06-10 |  | N
61 | Cost review (construction) | Third-party | R | Requested | Cost reviewer | 2026-06-08 |  | N | Lender-required for construction
62 | Borrower entity docs | Legal | R | Received | Counsel | 2026-05-15 | 2026-05-12 | Y
63 | Operating agreement | Legal | R | Received | Counsel | 2026-05-15 | 2026-05-12 | Y
64 | Certificate of good standing | Legal | R | Received | Counsel | 2026-05-18 | 2026-05-15 | Y
65 | EIN confirmation | Legal | R | Received | Counsel | 2026-05-12 | 2026-05-10 | Y
66 | Ownership chart | Legal | R | Reviewed | Counsel | 2026-05-15 | 2026-05-13 | Y
67 | KYC information | Legal | R | Received | Counsel | 2026-05-15 | 2026-05-13 | Y
68 | Litigation disclosure | Legal | R | Received | Counsel | 2026-05-15 | 2026-05-12 | Y | No material litigation
69 | Existing loan documents | Legal | - | N/A
70 | Purchase agreement | Legal | O | N/A |  |  |  |  | Construction, not acquisition
71 | GMP contract | Construction | R | Received | GC | 2026-05-22 | 2026-05-20 | Y | GMP $42M
72 | Construction contract | Construction | R | Received | GC | 2026-05-22 | 2026-05-20 | Y
73 | GC resume | Construction | R | Received | GC | 2026-05-15 | 2026-05-12 | Y
74 | Architect agreement | Construction | R | Received | Architect | 2026-05-15 | 2026-05-12 | Y
75 | Plans and specs | Construction | R | Received | Architect | 2026-05-18 | 2026-05-15 | Y | 100% CD set
76 | Permit status | Construction | R | Reviewed | GC | 2026-05-15 | 2026-05-12 | Y | All permits in hand
77 | Construction budget (detailed) | Construction | R | Reviewed | GC | 2026-05-22 | 2026-05-20 | Y
78 | Draw schedule (monthly) | Construction | R | Received | GC | 2026-05-22 | 2026-05-20 | Y
79 | Completion timeline | Construction | R | Received | GC | 2026-05-22 | 2026-05-20 | Y | 36-month
80 | Contingency budget | Construction | R | Reviewed | Analyst | 2026-05-22 | 2026-05-20 | Y | 5% hard cost contingency
81 | Builders risk insurance | Construction | R | Requested | Insurance broker | 2026-06-05 |  | N | Lender form on order
82 | Bonding info | Construction | O | N/A |  |  |  |  | Not required by lender
83 | Current insurance policy | Insurance/Tax | R | N/A |  |  |  |  | New construction
84 | Insurance quote (proposed) | Insurance/Tax | R | Requested | Insurance broker | 2026-06-05 |  | N
85 | Tax bills (3yr history) | Insurance/Tax | O | N/A |  |  |  |  | New construction
86 | Tax assessment | Insurance/Tax | R | Received | Sponsor | 2026-05-20 | 2026-05-18 | Y | Improvements assessment pending
87 | Abatement / PILOT documents | Insurance/Tax | O | N/A |  |  |  |  | No abatement
88 | Escrow requirements | Insurance/Tax | R | Needed | Lender | 2026-06-05 |  | N | Lender escrow form pending
89 | Flood zone determination | Insurance/Tax | R | Received | Sponsor | 2026-05-20 | 2026-05-18 | Y | Not in flood zone
90 | Funds flow | Closing | R | Needed | Lender | 2026-07-15 |  | N | Pre-closing
91 | Wire instructions | Closing | R | Needed | Lender | 2026-07-15 |  | N | Pre-closing
92 | Settlement statement | Closing | R | Needed | Title co | 2026-07-25 |  | N | Pre-closing
93 | Legal opinions | Closing | R | Needed | Counsel | 2026-07-25 |  | N | Pre-closing
94 | Resolutions | Closing | R | Needed | Counsel | 2026-07-20 |  | N
95 | Closing conditions checklist | Closing | R | Needed | Lender | 2026-07-15 |  | N | Pre-closing

## Document Tracker
Document Tracker
Filtered view of items that are NOT N/A. Use this for the weekly status call.
[6 empty] | Reviewed | Count
Item | Category | Status | Owner | Due | Notes | Reviewed | 0
Deal summary | Executive | Reviewed | Sponsor | 2026-05-10 |  | Not yet reviewed | 0
Property overview | Executive | Reviewed | Sponsor | 2026-05-10
Sources & uses | Executive | Reviewed | Sponsor | 2026-05-10
Loan request | Executive | Reviewed | Broker | 2026-05-10
Business plan summary | Executive | Reviewed | Sponsor | 2026-05-12
Capital stack | Executive | Reviewed | Sponsor | 2026-05-12
Timeline | Executive | Reviewed | Broker | 2026-05-14
Exit strategy | Executive | Received | Sponsor | 2026-05-15 | Refinance via miniperm
Key risks and mitigants | Executive | Received | Sponsor | 2026-05-15
Sponsor bio | Executive | Received | Sponsor | 2026-05-12
Property address | Property | Received | Sponsor | 2026-05-15
Parcel IDs | Property | Received | Sponsor | 2026-05-15
Site plan | Property | Reviewed | Sponsor | 2026-05-15
Survey | Property | Requested | Surveyor | 2026-06-15 | ALTA survey ordered 2026-05-15
Zoning report | Property | Reviewed | Sponsor | 2026-05-18 | MF-zoned, no variance needed
Floor plans | Property | Received | Architect | 2026-05-18
Property photos | Property | Received | Sponsor | 2026-05-15
Property management information | Property | Needed | Sponsor | 2026-06-01 | Property mgr selected; agreement TBD
Environmental Phase I | Property | Requested | Phase I provider | 2026-06-10 | Phase I engaged 2026-05-14
Stabilized pro forma | Financial | Reviewed | Analyst | 2026-05-15 | From UW Workbook
Construction budget | Financial | Reviewed | Sponsor | 2026-05-15 | $60.1M TPC
Sources & uses (detailed) | Financial | Received | Sponsor | 2026-05-15
Tax bills (current) | Financial | Received | Tax assessor | 2026-05-20
Insurance quotes | Financial | Requested | Insurance broker | 2026-06-05 | 3 carriers solicited
Acquisition / refi / construction purpose | Business plan | Reviewed | Sponsor | 2026-05-15
Leasing plan | Business plan | Received | Sponsor | 2026-05-20
Stabilization timeline | Business plan | Reviewed | Sponsor | 2026-05-20 | Year-3 stabilization
Permitting status | Business plan | Received | Sponsor | 2026-05-15 | All permits in hand
Construction timeline | Business plan | Reviewed | GC | 2026-05-22 | 36-month schedule
Draw schedule | Business plan | Received | GC | 2026-05-22
Sensitivity analysis | Business plan | Reviewed | Analyst | 2026-05-20 | From UW Workbook
Sponsor bio (detailed) | Sponsorship | Reviewed | Sponsor | 2026-05-12
Track record | Sponsorship | Reviewed | Sponsor | 2026-05-12 | 14 deals
Personal Financial Statement (PFS) | Sponsorship | Received | Sponsor | 2026-05-12 | PFS as of 2026-04-30
REO schedule | Sponsorship | Received | Sponsor | 2026-05-12 | 8 properties
Organizational chart | Sponsorship | Reviewed | Counsel | 2026-05-12
Entity documents | Sponsorship | Received | Counsel | 2026-05-15
Guarantor financials | Sponsorship | Received | Sponsor | 2026-05-12
Resume / project experience | Sponsorship | Reviewed | Sponsor | 2026-05-12
References | Sponsorship | Needed | Sponsor | 2026-06-05 | References list pending
Appraisal (lender-ordered) | Third-party | Requested | Appraiser | 2026-06-15 | Lender ordered 2026-05-18
Environmental Phase I (lender-reviewed) | Third-party | Requested | Phase I provider | 2026-06-10
Zoning report (lender-ordered) | Third-party | Requested | Zoning consultant | 2026-06-08
Survey (final certified) | Third-party | Requested | Surveyor | 2026-06-15
Title commitment | Third-party | Received | Title co | 2026-05-25
Insurance consultant review | Third-party | Requested | Insurance consultant | 2026-06-12 | Lender-required
Market study | Third-party | Requested | Market study consultant | 2026-06-10
Cost review (construction) | Third-party | Requested | Cost reviewer | 2026-06-08 | Lender-required for construction
Borrower entity docs | Legal | Received | Counsel | 2026-05-15
Operating agreement | Legal | Received | Counsel | 2026-05-15
Certificate of good standing | Legal | Received | Counsel | 2026-05-18
EIN confirmation | Legal | Received | Counsel | 2026-05-12
Ownership chart | Legal | Reviewed | Counsel | 2026-05-15
KYC information | Legal | Received | Counsel | 2026-05-15
Litigation disclosure | Legal | Received | Counsel | 2026-05-15 | No material litigation
GMP contract | Construction | Received | GC | 2026-05-22 | GMP $42M
Construction contract | Construction | Received | GC | 2026-05-22
GC resume | Construction | Received | GC | 2026-05-15
Architect agreement | Construction | Received | Architect | 2026-05-15
Plans and specs | Construction | Received | Architect | 2026-05-18 | 100% CD set
Permit status | Construction | Reviewed | GC | 2026-05-15 | All permits in hand
Construction budget (detailed) | Construction | Reviewed | GC | 2026-05-22
Draw schedule (monthly) | Construction | Received | GC | 2026-05-22
Completion timeline | Construction | Received | GC | 2026-05-22 | 36-month
Contingency budget | Construction | Reviewed | Analyst | 2026-05-22 | 5% hard cost contingency
Builders risk insurance | Construction | Requested | Insurance broker | 2026-06-05 | Lender form on order
Insurance quote (proposed) | Insurance/Tax | Requested | Insurance broker | 2026-06-05
Tax assessment | Insurance/Tax | Received | Sponsor | 2026-05-20 | Improvements assessment pending
Escrow requirements | Insurance/Tax | Needed | Lender | 2026-06-05 | Lender escrow form pending
Flood zone determination | Insurance/Tax | Received | Sponsor | 2026-05-20 | Not in flood zone
Funds flow | Closing | Needed | Lender | 2026-07-15 | Pre-closing
Wire instructions | Closing | Needed | Lender | 2026-07-15 | Pre-closing
Settlement statement | Closing | Needed | Title co | 2026-07-25 | Pre-closing
Legal opinions | Closing | Needed | Counsel | 2026-07-25 | Pre-closing
Resolutions | Closing | Needed | Counsel | 2026-07-20
Closing conditions checklist | Closing | Needed | Lender | 2026-07-15 | Pre-closing

## Data Room Index
Data Room Index
Maps to the actual folder structure being uploaded. File-naming convention: [Property]_[Doc Type]_[YYYY-MM-DD].pdf
Folder | Subfolder | File name | Date uploaded | Version | Access | Notes
1_Executive | Cover memo + exec summary
2_Property | Address, photos, plans, surveys, zoning
3_Financial | T-12, pro forma, rent roll, S&U, tax bills
4_Business_Plan | Renovation, leasing, stabilization, sensitivity
5_Sponsorship | Sponsor bio, track record, PFS, REO, org chart, KYC
6_Third_Party | Appraisal, environmental, PCA, market study, cost review
7_Legal | Entity docs, operating agreement, COGS, EIN, KYC
8_Construction | GMP, plans, permits, draw schedule, contingency
9_Insurance_Tax | Insurance quote, tax bills, abatement docs, flood det
10_Closing | Funds flow, wire, settlement, legal opinions

## Missing Items
Missing Items
Items with status = Needed and required for the active loan type. Drives the next-action list.
Item | Category | Owner | Due | Notes
References | Sponsorship | Sponsor | 2026-06-05 | References list pending
Escrow requirements | Insurance/Tax | Lender | 2026-06-05 | Lender escrow form pending
Funds flow | Closing | Lender | 2026-07-15 | Pre-closing
Wire instructions | Closing | Lender | 2026-07-15 | Pre-closing
Settlement statement | Closing | Title co | 2026-07-25 | Pre-closing
Legal opinions | Closing | Counsel | 2026-07-25 | Pre-closing
Resolutions | Closing | Counsel | 2026-07-20
Closing conditions checklist | Closing | Lender | 2026-07-15 | Pre-closing

## Lender Q&A
Lender Q&A
Every lender question, logged. The diligence audit trail.
Question | Lender contact | Asked | Category | Owner | Status | Answer | Answered | File?
Confirm sponsor's other active projects + capacity | Bank A | 2026-05-20 | Sponsorship | Sponsor | Answered | Latham Capital has 6 active projects, all on schedule. Sponsor capacity confirmed via PFS. | 2026-05-22 | Y
Provide updated unit mix and projected rents | Bank A | 2026-05-20 | Business plan | Analyst | Answered | Updated rent assumptions included in pro forma; market study supports. | 2026-05-21 | Y
Insurance cost detail and lender form compliance | Bank A | 2026-05-22 | Insurance/Tax | Insurance broker | Open | Awaiting carrier quotes + lender form review by consultant. |  | N
Updated stabilized real estate tax estimate | Bank A | 2026-05-22 | Insurance/Tax | Analyst | Open | Improvements assessment pending; expected within 30 days. |  | N
GC bonding capacity confirmation | Bank A | 2026-05-23 | Construction | GC | Answered | GC carrying $80M aggregate bonding; this project at $42M. Surety letter provided. | 2026-05-24 | Y

## Submission Log
Submission Log
Every submission to the lender, timestamped. Audit-trail discipline.
Date | Items submitted | Submitted by | Receipt confirmed? | Lender follow-up
2026-05-12 | Executive package + sponsor bio + PFS/REO | Latham Capital | Y | 5 follow-up Qs (see Q&A tab)
2026-05-22 | Construction docs + GMP + plans + budget | GC + Sponsor | Y | 1 follow-up on bonding (resolved)