## Instructions
Renovation Budget Builder · Instructions
Version 1.0
HOW TO USE
1. Start with Project Summary tab -- fill yellow cells first.
2. Fill per-category budget tabs (Unit Renovation, Common Area, Exterior, Soft Costs).
3. Contingency tab tracks hard / soft / owner reserves.
4. Draw Schedule projects monthly spend through the renovation period.
5. Budget Rollup shows the IC-ready category summary -- share this with your lender.
6. Variance tab tracks budget vs actual over the project life.
7. Cost Overrun Sensitivity tests deal economics at different overrun scenarios.
8. Lender Summary tab prints to one letter page.
Tip: yellow cells are required fields. Budget Rollup and Lender Summary auto-populate.
Navigation: 12 tabs total -- use Ctrl+PgDn / Ctrl+PgUp to move between tabs.

## Project Summary
Project Summary
Top-level project info. Drives downstream calcs.
PROJECT
Property name | Dallas Garden VA
Units (total) | 200
Units to be renovated | 160
Budget per unit ($) | 24000
Common area budget | 450000
Exterior / site work | 850000
Soft costs | 720000
Hard contingency % | 5%
Soft contingency % | 5%
Owner contingency | 200000
Project months | 14
% funded by loan | 50%
COMPUTED TOTALS
Unit renovation total | 0
Hard cost subtotal | 0
Hard contingency | 0
Soft contingency | 0
Total contingency (incl owner) | 0
TOTAL BUDGET | 0
$/unit (all-in) | 0

## Unit Renovation
Unit Renovation Budget
Per-unit scope. Cost per unit x units affected = total.
Scope item | Units affected | Cost / unit | Total cost | Notes
Flooring (LVP / carpet) | 160 | 3200 | 0 | Vinyl plank kitchens + carpet bedrooms
Paint (walls + trim) | 160 | 1400 | 0 | Two coats, full unit
Cabinets (reface or replace) | 160 | 4500 | 0 | Reface in 70%, replace in 30%
Countertops (quartz) | 160 | 2100 | 0 | Quartz in all kitchens
Appliances (stainless) | 160 | 2400 | 0 | Range + DW + fridge + MW
Bathroom fixtures | 160 | 1800 | 0 | Vanity + toilet + shower
Lighting (LED conversion) | 160 | 800 | 0 | All fixtures
Doors / hardware | 160 | 600 | 0 | Interior doors only
Plumbing fixtures | 160 | 700 | 0 | Faucets, valves
Electrical | 160 | 500 | 0 | Outlets, switches, USB outlets
HVAC refresh | 160 | 1400 | 0 | Filter + service, no replacement
Smart-home + misc | 160 | 600 | 0 | Locks + thermostats
Window treatments | 160 | 400 | 0 | Blinds
Misc / soft scope | 160 | 1300 | 0 | Buffer for surprises
TOTAL |  |  | 0

## Common Area
Common Area Budget
Scope item | Amount | Notes
Lobby / leasing office | 180000
Hallways / corridors | 120000
Amenity rooms (clubroom) | 90000
Fitness center | 40000
Laundry | 20000
TOTAL | 0

## Exterior
Exterior Budget
Scope item | Amount | Notes
Roof repairs / coating | 320000
Parking lot resurface | 240000
Landscaping refresh | 110000
Site lighting | 60000
Pool / spa refresh | 80000
Misc site work | 40000
TOTAL | 0

## Soft Costs
Soft Costs Budget
Scope item | Amount | Notes
Architecture | 120000
Engineering | 80000
Permits | 130000
Legal | 60000
Insurance (builders risk) | 110000
Project management | 130000
Testing / inspection | 50000
Other soft | 40000
TOTAL | 0

## Contingency
Contingency Tracker
Track each contingency draw with reason and balance remaining.
CONTINGENCY POOLS
Hard contingency (initial) | 0
Soft contingency (initial) | 0
Owner contingency (initial) | 0
Total contingency | 0
DRAW LOG
Date | Amount | Reason - approved by

## Draw Schedule
Monthly Draw Schedule
Project month, budgeted spend, actual, variance.
Month | Budgeted spend | Actual spend | Cumulative actual | Remaining budget | Notes
Month 1 | 0 |  | 0 | 0
Month 2 | 0 |  | 0 | 0
Month 3 | 0 |  | 0 | 0
Month 4 | 0 |  | 0 | 0
Month 5 | 0 |  | 0 | 0
Month 6 | 0 |  | 0 | 0
Month 7 | 0 |  | 0 | 0
Month 8 | 0 |  | 0 | 0
Month 9 | 0 |  | 0 | 0
Month 10 | 0 |  | 0 | 0
Month 11 | 0 |  | 0 | 0
Month 12 | 0 |  | 0 | 0
Month 13 | 0 |  | 0 | 0
Month 14 | 0 |  | 0 | 0

## Variance
Budget Variance
Original vs revised vs actual. Sort by absolute variance.
Line item | Original budget | Revised budget | Actual cost | Variance / Reason

## Cost Overrun
Cost Overrun Sensitivity
Overrun % x Contingency size -- Equity rebalance required.
OVERRUN x CONTINGENCY -- EQUITY GAP
Contg % \ Overrun | 0% | 5% | 10% | 15% | 20%
3% | 0 | 0 | 0 | 0 | 0
5% | 0 | 0 | 0 | 0 | 0
7% | 0 | 0 | 0 | 0 | 0
10% | 0 | 0 | 0 | 0 | 0
15% | 0 | 0 | 0 | 0 | 0

## Lender Summary
Lender Summary Output
Print-ready summary. Distribute to lender / IC.
Property | 0
Scope | 0
Total budget | 0
$/unit (all-in) | 0
Hard / soft / contingency | 0
Timeline | 0
Funding source split | 0

## Budget Rollup
Budget Rollup -- By Category
Consolidated budget by category with % of total. IC-ready overview.
CATEGORY BREAKDOWN
Category | Budget | % of Total
Unit Renovation | 0 | 0%
Common Area | 0 | 0%
Exterior / Site | 0 | 0%
Soft Costs | 0 | 0%
Hard Contingency | 0 | 0%
Soft Contingency | 0 | 0%
Owner Contingency | 0 | 0%
TOTAL BUDGET | 0 | 100.0%
0 | 0