## Instructions
Transaction Timeline Builder · Instructions
Version 1.0
1. Set deal-type variant (drives initial task list).
2. Edit start dates on Master Timeline tab.
3. Critical Path filters to no-float tasks.
4. Responsibility Matrix assigns ownership.
5. Summary tab prints to one page.
6. Calendar Export tab is ICS / Google Cal-compatible.

## Master Timeline
Master Timeline
Every task. Sort and filter as needed.
Status legend: | Reviewed / Received | Pending / Requested | Not started | Priority H | Priority M
Task | Category | Start | Due | Owner | Status | Priority | Days remaining | Notes
Term sheet executed | Financing | 2026-05-25 | 2026-05-26 | Sponsor | Reviewed | H | 0
Lender application + KYC | Legal | 2026-06-01 | 2026-06-04 | Counsel | Received | H | 0
Entity docs to lender | Legal | 2026-06-03 | 2026-06-06 | Counsel | Received | H | 0
Appraisal engaged | Third-party | 2026-06-04 | 2026-06-05 | Sponsor | Requested | H | 0
Environmental Phase I engaged | Third-party | 2026-06-04 | 2026-06-05 | Sponsor | Requested | H | 0
PCA engaged | Third-party | 2026-06-04 | 2026-06-05 | Sponsor | Requested | M | 0
Survey engaged | Third-party | 2026-06-04 | 2026-06-05 | Sponsor | Requested | H | 0
Title commitment | Third-party | 2026-06-06 | 2026-06-09 | Title co | Received | H | 0
Insurance quote solicited | Insurance | 2026-06-08 | 2026-06-13 | Insurance broker | Requested | H | 0
Zoning report engaged | Third-party | 2026-06-08 | 2026-06-11 | Counsel | Requested | M | 0
GC contract executed | Construction | 2026-06-09 | 2026-06-12 | GC | Received | H | 0
Plans + specs final review | Construction | 2026-06-11 | 2026-06-16 | Architect | Received | H | 0
Permits confirmed in hand | Construction | 2026-06-13 | 2026-06-15 | Sponsor | Reviewed | H | 0
Appraisal delivered | Third-party | 2026-06-22 | 2026-06-23 | Appraiser | Requested | H | 0
Phase I delivered | Third-party | 2026-06-15 | 2026-06-16 | Phase I provider | Requested | H | 0
PCA delivered | Third-party | 2026-06-18 | 2026-06-19 | PCA provider | Requested | M | 0
Survey delivered (ALTA) | Third-party | 2026-06-22 | 2026-06-23 | Surveyor | Requested | H | 0
Insurance bound | Insurance | 2026-06-22 | 2026-06-25 | Insurance broker | Pending | H | 0
Loan agreement first draft | Legal | 2026-06-21 | 2026-07-01 | Counsel | Pending | H | 0
Borrower review of loan agree | Legal | 2026-06-29 | 2026-07-04 | Sponsor | Pending | H | 0
Loan agreement final | Legal | 2026-07-06 | 2026-07-11 | Counsel | Not started | H | 0
Funds flow drafted | Closing | 2026-07-16 | 2026-07-19 | Counsel | Not started | H | 0
Wire instructions confirmed | Closing | 2026-07-19 | 2026-07-20 | Lender | Not started | H | 0
Insurance certificates to lender | Closing | 2026-07-21 | 2026-07-23 | Insurance broker | Not started | H | 0
Settlement statement | Closing | 2026-07-23 | 2026-07-25 | Title co | Not started | H | 0
Legal opinions delivered | Closing | 2026-07-26 | 2026-07-27 | Counsel | Not started | H | 0
CLOSE + Notice to Proceed | Closing | 2026-07-31 | 2026-08-01 | All | Not started | H | 0
Formulas:
Days remaining = [Not started]-TODAY()

## Critical Path
Critical Path
Tasks where completion delays will delay closing.
Task | Due date | Owner | Status | Days remaining
Term sheet executed | 2026-05-26 | Sponsor | Reviewed | 0
Lender application + KYC | 2026-06-04 | Counsel | Received | 0
Entity docs to lender | 2026-06-06 | Counsel | Received | 0
Appraisal engaged | 2026-06-05 | Sponsor | Requested | 0
Environmental Phase I engaged | 2026-06-05 | Sponsor | Requested | 0
Survey engaged | 2026-06-05 | Sponsor | Requested | 0
Title commitment | 2026-06-09 | Title co | Received | 0
Insurance quote solicited | 2026-06-13 | Insurance broker | Requested | 0
GC contract executed | 2026-06-12 | GC | Received | 0
Plans + specs final review | 2026-06-16 | Architect | Received | 0
Permits confirmed in hand | 2026-06-15 | Sponsor | Reviewed | 0
Appraisal delivered | 2026-06-23 | Appraiser | Requested | 0
Phase I delivered | 2026-06-16 | Phase I provider | Requested | 0
Survey delivered (ALTA) | 2026-06-23 | Surveyor | Requested | 0
Insurance bound | 2026-06-25 | Insurance broker | Pending | 0
Loan agreement first draft | 2026-07-01 | Counsel | Pending | 0
Borrower review of loan agree | 2026-07-04 | Sponsor | Pending | 0
Loan agreement final | 2026-07-11 | Counsel | Not started | 0
Funds flow drafted | 2026-07-19 | Counsel | Not started | 0
Wire instructions confirmed | 2026-07-20 | Lender | Not started | 0
Insurance certificates to lender | 2026-07-23 | Insurance broker | Not started | 0
Settlement statement | 2026-07-25 | Title co | Not started | 0
Legal opinions delivered | 2026-07-27 | Counsel | Not started | 0
CLOSE + Notice to Proceed | 2026-08-01 | All | Not started | 0
Formulas:
Days remaining = [Due date]-TODAY()

## Diligence
Diligence Tracker
Diligence item | Vendor | Engaged date | Expected | Status | Cost
Appraisal
Environmental Phase I
PCA
Survey (ALTA)
Title commitment
Zoning report
Insurance review
Tax review
Budget review (GC)
Cost reviewer
Market study

## Closing
Closing Checklist
Item | Owner | Due | Status | Notes
Loan documents (executed)
Entity docs
Insurance certificates
Title policy
Survey (final)
Funds flow
Wire instructions
Settlement statement
Legal opinions
Resolutions
Closing conditions met

## RACI Matrix
Responsibility Matrix (RACI)
R=Responsible A=Accountable C=Consulted I=Informed
Task | Sponsor | Broker | Lender | Counsel | Title | Insurance | GC | Consultant
Term sheet executed | A | R | C | C
Lender application + KYC | R | C | A | C
Entity docs to lender | R |  | I | A
Appraisal engaged | R |  | I |  |  |  |  | A
Environmental Phase I engaged | R |  | I |  |  |  |  | A
Title commitment | C |  | I | A | R
Insurance quote solicited | A |  | I |  |  | R
GC contract executed | A |  | I | C |  |  | R
Plans + specs final review | A |  | C |  |  |  | R | C
Permits confirmed in hand | R |  | I | C
Appraisal delivered | C |  | I |  |  |  |  | R
Insurance bound | A |  | I |  |  | R
Loan agreement final | A | C | A | R
Funds flow drafted | C |  | C | R | C
Settlement statement | C |  | C | C | R
CLOSE + Notice to Proceed | R | C | A | C | C | I | I | I
Wire instructions confirmed | R: R; A: A; C: C
Legal opinions delivered | R: C; A: I; C: R
Diligence items (general) | R: A; A: I; C: C; I: R
Survey engaged | R: R; A: I; C: C
Phase I delivered | R: C; A: I; I: R
Zoning report engaged | R: A; A: I; C: R
PCA engaged | R: R; A: I; I: A
Closing conditions met | A | C | A | R | C | I | I | I
Insurance certificates to lender | R A: A; I A: I; I I: R
Borrower review of loan agree | R A: R; R C: C; I A: I; I R: A
PCA delivered | R A: C; I A: I; A I: R

## Calendar
Calendar Export
Copy as CSV → import to your calendar of choice.
Event | Date | Time | Owner | Category
Term sheet executed | 2026-05-26 | 09:00 | Sponsor | Financing
Lender application + KYC | 2026-06-04 | 09:00 | Counsel | Legal
Entity docs to lender | 2026-06-06 | 09:00 | Counsel | Legal
Appraisal engaged | 2026-06-05 | 09:00 | Sponsor | Third-party
Environmental Phase I engaged | 2026-06-05 | 09:00 | Sponsor | Third-party
PCA engaged | 2026-06-05 | 09:00 | Sponsor | Third-party
Survey engaged | 2026-06-05 | 09:00 | Sponsor | Third-party
Title commitment | 2026-06-09 | 09:00 | Title co | Third-party
Insurance quote solicited | 2026-06-13 | 09:00 | Insurance broker | Insurance
Zoning report engaged | 2026-06-11 | 09:00 | Counsel | Third-party
GC contract executed | 2026-06-12 | 09:00 | GC | Construction
Plans + specs final review | 2026-06-16 | 09:00 | Architect | Construction
Permits confirmed in hand | 2026-06-15 | 09:00 | Sponsor | Construction
Appraisal delivered | 2026-06-23 | 09:00 | Appraiser | Third-party
Phase I delivered | 2026-06-16 | 09:00 | Phase I provider | Third-party
PCA delivered | 2026-06-19 | 09:00 | PCA provider | Third-party
Survey delivered (ALTA) | 2026-06-23 | 09:00 | Surveyor | Third-party
Insurance bound | 2026-06-25 | 09:00 | Insurance broker | Insurance
Loan agreement first draft | 2026-07-01 | 09:00 | Counsel | Legal
Borrower review of loan agree | 2026-07-04 | 09:00 | Sponsor | Legal
Loan agreement final | 2026-07-11 | 09:00 | Counsel | Legal
Funds flow drafted | 2026-07-19 | 09:00 | Counsel | Closing
Wire instructions confirmed | 2026-07-20 | 09:00 | Lender | Closing
Insurance certificates to lender | 2026-07-23 | 09:00 | Insurance broker | Closing
Settlement statement | 2026-07-25 | 09:00 | Title co | Closing
Legal opinions delivered | 2026-07-27 | 09:00 | Counsel | Closing
CLOSE + Notice to Proceed | 2026-08-01 | 09:00 | All | Closing

## Summary
Timeline Summary
Single-page status. Print landscape.
DEAL STATUS
Target close date | 2026-07-31
Total tasks | 0
Completed | 0
Pending / requested | 0
Not started | 0
HIGH-RISK ITEMS
Critical path: appraisal, environmental, GMP contract, title commitment all on schedule. Loan agreement first draft is the most-likely delay vector.
COMPLETION BY CATEGORY
Category | Completed
Financing | 1
Legal | 2
Third-party | 1
Construction | 3
Insurance | 0
Closing | 0